## FRD List
FRD No. | FRD Description | FDD Description | Sheet No. | Type | Technical Effort (Hrs) | Technical Assigned | Start Date | End Date | Technical Status | Functional Testing By | Functional Testing Status | CRP Ststus | Remarks
FRD/RC/CST-003 | Food cost and cost allocation | Project wise cost | c1 | Customization
|  | Enter project detail | j1 | Customization | 4 | Suraj | 2020-03-26 | 2020-03-26 | Done | Santhosh | Done
FRD/RC/SAL-001 | Sales cycle (Event) | Banquet enquiry and validation | j1 | Customization | 7 | Suraj |  |  | Done | Santhosh | Done
FRD/RC/SAL-001 | Sales cycle (Contract) | Create Banquet Event Order | s1 | Customization | 24 | Suraj | 2020-03-27 | 2020-03-31 | Done | Santhosh | Done |  | p2: Copy Functionality: Order date; Posting Date; Shipment Date; Date of Funcion Start and Date of Function End (Should not change or update) | TODO
FRD/RC/CST-003 | Food cost and cost allocation | Production plan | c2 | Customization | 14 | Sunil | 2020-03-26 | 2020-03-27 | Done | Santhosh | Done
FRD/RC/CST-003 | Food cost and cost allocation | Auto cost booking (Trf to CPU Kitchen/Project Kitchen) | c3 | Customization | 10 | Sunil | 2020-03-30 | 2020-03-31 | Done | Santhosh | Done
FRD/RC/CST-003 | Food cost and cost allocation | Auto cost booking (Direct purchase at CPU Kitchen/Project Kitchen) | c4 | Customization | 20 | Sunil | 2020-04-01 | 2020-04-03 | Done | Santhosh | Done
FRD/RC/CST-003 | Food cost and cost allocation | Cost sheet report and Journal Posting | c5 | Customization | 16 | Suraj | 2020-04-01 | 2020-04-02 | Done | Santhosh | Done
FRD/RC/PUR-001 | Purchase cycle | Purchase requisition workflow and approval | p1 | Customization | 20 | Suraj | 2020-04-03 | 2020-04-07 | Done | Santhosh | Done |  |  | p1: Item description
FRD/RC/PUR-001 | Purchase cycle | Transfer order requisition workflow and approval |  | Customization
FRD/RC/PUR-001 | Purchase cycle | Request for Quote |  | Customization | 10 | Suraj | 2020-04-08 | 2020-04-09
FRD/RC/PUR-001 | Purchase cycle | Purchase order - Send to Vendor status and send mail through outlook. | p2 | Customization | 10 | Sunil | 2020-04-06 | 2020-04-07 | Done | Santhosh | Done |  | Mail body structure; Salutation; Signature
FRD/RC/PUR-001 | Purchase cycle | Purchase order approval based on Trade Price exist or Not. | p3 | Customization | 10 | Sunil | 2020-04-07 | 2020-04-08 | Done | Santhosh | Done
FRD/RC/PUR-001 | Purchase cycle | Rejected Qty Field and Auto Trf. To Reject Location | p4 | Customization | 14 | Sunil | 2020-04-09 | 2020-04-10 | Done | Santhosh | Done
FRD/RC/PUR-001 | Purchase cycle | Over delivery | p5 |  | 14 | Suraj | 2020-04-10 | 2020-04-13 | Done | Santhosh | Inprocess |  | need to take call with selva for confirmation the process which we have taken , and PO report to be modified after the confimation.
FRD/RC/PUR-001 | Purchase cycle | Short delivery (Close PO Process) | p6 |  | 10 | Suraj | 2020-04-13 | 2020-04-14 | Done | Santhosh | Inprocess
FRD/RC/MAN-001 | Maintenance service | Maintenance service | m1 | Customization | 12 | Suraj | 2020-04-15 | 2020-04-16
FRD/RC/FIN-003 | Post Dated Cheque | Process of Post dated cheque | f1 | Customization | 20 | Sunil | 2020-04-13 | 2020-04-15
| Facility management | Facility management (Fields requred for sales invoice) |  | Customization | 4 | Sunil | 2020-04-16 | 2020-04-16
| General Journal Workflow | General Journal Workflow (Batch Customization) Copy from VX Studio |  | Customization | 10 | Sunil | 2020-04-16 | 2020-04-17
| Fixed Asset | Fixed asset as inventory item | f2 | Customization | 14 | Suraj | 2020-04-17 | 2020-04-20
FRD/RC/RP-001 | Delivery Note |  | r1 | Reports | 16 | Suraj | 2020-04-21 | 2020-04-22 | Inprocess | Santhosh | Inprocess
FRD/RC/RP-001 | Event Order Sheet (BEO) |  | r2 | Reports | 20 | Suraj | 2020-04-23 | 2020-04-27 | Done | Santhosh | Inprocess |  | p1: BEO report print option in Print/Send Button avbl in front. P1: BEO report A4 size print p1: BEO report (correction required: Need to share the details)
FRD/RC/RP-001 | Tax Invoice |  | r3 | Reports | 16 | suraj |  |  | Inprocess | Pradeep | Inprocess |  | Remark Sent for Changes p3: Customer phone no; Posted tax invoice no; VAT Amount; Amount in words
FRD/RC/RP-001 | Tax Invoice (facility Management) |  | r77 | Reports | 12 | Sunil | 2020-04-22 | 2020-04-23
FRD/RC/RP-001 | Catch Invoice |  | r4 | Reports | 10 | Sunil | 2020-04-23 | 2020-04-24
FRD/RC/RP-001 | Item Journal |  | r5 | Reports | 16 | Suraj | 2020-04-28 | 2020-04-29 | Done | Pradeep | Done
FRD/RC/RP-001 | packing slip summary |  | r6 | Reports | 12 | Suraj | 2020-04-30 | 2020-05-01
FRD/RC/RP-001 | packing slip |  | r7 | Reports | 10 | Suraj | 2020-05-01 | 2020-05-04 | Inprocess | Pradeep | Inprocess |  | Remark send Some for Changes in Standard Report
FRD/RC/RP-001 | sales order |  | r8 | Reports |  | Sunil |  |  | Done | Pradeep | Done
FRD/RC/RP-001 | Transfer order-Shipment |  | r9 | Reports | 10 | Sunil | 2020-04-27 | 2020-04-28 | Inprocess | Pradeep | Inprocess |  | Remark send Some for Changes in Standard Report
FRD/RC/RP-001 | Cost Allocation |  | r10 | Reports | 16 | Sunil | 2020-04-28 | 2020-04-30 | Done | Santhosh | Inprocess
FRD/RC/RP-001 | Purchase Order |  | r12 | Reports | 10 | Suraj |  |  | Completed | Pradeep | Inprocess |  | Remark Sent for Changes P3: Correction required: VAT Amount, Amount in Word.
FRD/RC/RP-001 | Category wise/Vendor wise/UoM Wise Item Qty and Cost |  | r13 | Reports | 16 | Suraj | 2020-05-05 | 2020-05-06
FRD/RC/RP-001 | Breakdown monitoring report (Maintenance) |  | r14 | Reports | 14 | Suraj | 2020-05-07 | 2020-05-08
FRD/RC/RP-001 | Check Printing Report • AL Mashraf Bank-Arbift (Format Shared) • NBF Bank (Format Shared) |  | r15 | Reports | 10 | Suraj | 2020-05-09 | 2020-05-10
FRD/RC/RP-001 | PDC Register |  | r16 | Reports | 8 | Sunil | 2020-05-01 | 2020-05-01
FRD/RC/RP-001 | Voucher print | Copy from VX Studio | r18 | Reports | 10 | Sunil | 2020-05-04 | 2020-05-05
FRD/RC/RP-001 | Tax Register |  |  | Reports | 10 | Sunil | 2020-05-05 | 2020-06-06 |  |  |  |  | Format /Column not finalised
FRD/RC/RP-001 | Average price per item |  |  | Reports | 10 | Sunil | 2020-05-07 | 2020-05-08
469

## c1
FRD List
Food cost and cost allocation-Project wise cost
1.1 For any new contract/project dimension is created.
1.2 Account schedule will be used for Project wise revenue and expenses.
1.3 System should also provide, project wise sales invoice; BEO; purchases (if direct purchase); item journal.
While configuration/customization, should keep in mind, possibility of generating following data/report (other than mentioned in FRD)
Project wise invoice and receipt.
Project wise BEO list.
Project wise item journal detail.
Project wise direct purchase order.
Project wise JV expenses.
Project wise revenue and expense report from sales; General ledger and item ledger table.

## j1
FRD/RC/CST-003-1.1 | Project Dimension and Project Mapping
Custom table to maintain project dimension wise default value.
Either a custom table or Base Project table to capture the following default details:
| Project start date |  |  |  |  | LOC001 |  | LoC010
| Project end date | [6 empty] | Location=Kitchen
| Project status | Open; Inporcess; Hold; Closed |  | Scenario | WH | Bulk Kitchen |  | Project Location
| Kitchen Location |  |  |  |  | Processs Food
| Project Location |  | New
[5 empty] | Mineral water | > | >
Only one project dimension + project combination should exit in system.
Table
| Project Dimension | Project No.
Ferrari World

## S1
FRD/RC/SAL-001 | Sales cycle (Banquet Event Order)
Sales order Header:
Type of Sale: | Event; Contract; Counter Sale; Facility Management; Others |  |  | (Separate Page for Each Type)
Type of sale is mandatory field and will be used for validation.
• Fill Contract Details
• Require Custom from | Custom
• In Sales Header (Customise Field)-Update BEO Status require Given Option-: Inquiry; Tentative; Definite; Full Delivered; Partial Delivered; Cancelled; Turn Down; Full Invoiced; Partial Invoiced | Custom |  |  | If Status = Released, then auto change to Definite. Partial Delivered, if sales order line delivery is pending. Full Delivered, if completely shipped = Yes Partial Invoiced, if sales orer line invoice is pending. Full Invoiced, if Status = Invoiced. |  | Status of Event (on BEO Enquiry form and Transaction Status on BEO Order Field)
• In Sales Header BEO version to be Maitain (On any Modifiaction) .i.e. Version 1, 2 | Base archive version to be used.
• In Sales order form (Above) option require (i.e. Copy BEO Information) (Information that captured in previouse BEO -Same Project | Custom
Fields Name | Type | No. of Line | No. of Characters | Remarks | Column1 | Tab | Sequence | Column2 | New Fields
Sales Order Number / BEO # | No. Series | NA | NA | No. Series |  | General | 1
Type of Sale |  |  |  | Option Field : Event; Contract; Counter Sale; Facility Management; Others (Default on Sales Order) |  | General | 1 |  | Already Mention above
Organization Name | Automatic' |  |  | Sales order > Customer Card |  | General-Customer Info | 1
Contact Name | Customer Card | NA | NA | Customer Card |  | General-Customer Info | 2
Phone Numbers: | Customer Card | NA | NA | Customer Card |  | General-Customer Info | 3
Email Address: | Customer Card | NA | NA | Customer Card |  | General-Customer Info | 4
SalesPerson | Sales order | NA | NA | Sales order > Sales person |  | General-Customer Info | 5
Prepared by: | Lookup field |  |  | Sales order > Assigned User ID |  | General-Customer Info | 5
Method of Receiving Enquiry | List Field |  |  | Note: Option to add to this list Telephone | New Table | General-Customer Info | 6
Status Field |  |  |  | Option Field: Inquiry; Tentative; Definite; Full Delivered; Partial Delivered; Cancelled; Turn Down; Full Invoiced; Partial Invoiced |  | General | 2
Revision | Revision | NA | NA |  |  | General | 2
Project ID | Dimension | NA | NA |  |  | General | 3
Project Name | Dimension Name | NA | NA |  |  | General | 4
date of function start: | Date Filed | NA | NA |  |  | General | 5
date of function end: | Date Filed | NA | NA |  |  | General | 6
Start Timing: | Text Fields | 5 | 50 |  |  | General | 7
End Timing: | Text Fields | 5 | 50 |  |  | General | 8
Order date |  | NA | NA | Sales order > Order Date |  | General | 9 |  | New
Posting date |  | NA | NA | Sales order > Posting Date |  | General | 10 |  | New
Project Location Code |  |  |  | From Project |  | General |  |  | New
Kitchen Location |  |  |  | From Project |  | General |  |  | New
Event | Text Fields | 1 | 100 |  |  | Event Info | 1
Details of the event | Text Fields | 10 | 100 |  |  | Event Info | 2
Type of Event | List Filed |  |  | Note: Option to add to this list Type of Event: Breakfast; Lunch; Dinner; Coffee Break; Parcels; Reception; Equipment Rental; Iftar Ramadan; Sohour Ramadan; Local Food Delivery; 1 Coffee and Lunch; 2 Coffee Breaks and Lunch; 2 Coffee Breaks | New Table | Event Info
Type of Event (Brief) | Text Fields |  | 100 |  |  | Event Info
Segment | List Field |  |  | Note: Option to add to this list Blanket agreement; Event-Contract; Corporate; Government; Private Event. | New Table | Event Info
Venue: | Text Fields | 1 | 100 |  |  | Event Info | 1
Location (BEO): | Text Fields | 1 | 100 |  |  | Event Info | 2
Guest Guaranteed | Text Fields | 5 | 50 Each Line |  |  | Guests | 1
Guest Expexted | Text Fields | 5 | 50 Each Line |  |  | Guests | 2
No. of PAX | No. Field |  |  | User will enter manually in this field. |  | Pricing and Billing (Revenue Report)
Average Price Per PAX/F&B | Amount Field |  |  | User will enter manually in this field. |  | Pricing and Billing (Revenue Report)
Transport (Amount) | Amount Field |  |  | User will enter manually in this field. |  | Pricing and Billing (Revenue Report)
Staff (Amount) | Amount Field |  |  | User will enter manually in this field. |  | Pricing and Billing (Revenue Report)
Menu Price | Text Fields | 1 | 100 |  |  | Pricing and Billing | 1
Pricing | Text Fields | 10 | 100 |  |  | Pricing and Billing
Billing Instruction: | Text Fields | 5 | 100 |  |  | Pricing and Billing
Service Delivery | Text Fields | 10 | 100 |  |  | Event Info | 5
Service Style | Text Fields | 10 | 100 |  |  | Event Info | 5
HK Lines | Text Fields | 10 | 100 |  |  | Guests | 3 |  | New
Food Menus: | Text Fields | 100 | 5000 |  |  | Food and Beverage | 1
Beverages: | Text Fields | 50 | 50 |  |  | Food and Beverage | 2
Food & Beverages Notes: | Text Fields | 10 | 100 |  |  | Food and Beverage | 3
Kithcen: | Text Fields | 10 | 100 |  |  | Setup And Equipment Notes | 6
Equipment: | Text Fields | 10 | 100 |  |  | Setup And Equipment Notes | 8
Stewarding: | Text Fields | 10 | 100 |  |  | Setup And Equipment Notes | 9
Restriction/Special Reference | Text Fields | 10 | 100 |  |  | Setup And Equipment Notes | 2
Setup notes: | Text Fields | 10 | 100 |  |  | Setup And Equipment Notes | 1
Staffing: | Text Fields | 10 | 100 |  |  | Setup And Equipment Notes | 10
Housekeeping | Text Fields | 10 | 100 |  |  | Setup And Equipment Notes | 12
Transportation/Security | Text Fields | 10 | 100 |  |  | Setup And Equipment Notes | 15
Engineering | Text Fields | 10 | 100 |  |  | Setup And Equipment Notes | 13
Additional Instructions | Text Fields | 10 | 100 |  |  | Setup And Equipment Notes | 14
Reffered By | Text Fields | 1 | 100 |  |  | Setup And Equipment Notes | 3 |  | New
Hygiene | Text Fields | 10 | 100 |  |  | Setup And Equipment Notes | 11 |  | New
BEO Meal Line Detail:
Separate BEO Meal line for each date and meal.
BEO Line with No. of PAX, Price Per PAX Optional.
Non-inventory item to be mentained for each meal type like Breakfast; Lunch; Coffee Break1 etc.
Fields:
Delivery Date: | Heading change (Shipment Date to Delivery date)
No. | Each menu will be created as non-inventory item. Lookup of menu item only.
Production Plan No. | One sales order line = One Production Plan. (When Production Plan is created against a BEO Meal line, system update this field).
Production Plan Qty
On Shipment posting:
Qty. to ship + Qty Shipped should be less than or equal to Production Plan Qty.
Qty to Ship line (Delivery Date = Posting Date) If sales type = Event; Contract; Counter Sale
Delivery Date | Type | No. | Description | Location Code | Quantity | Unit of Measure Code | Unit Price Excl. VAT | Line Amount Excl. VAT | Qty. to Ship | Qty. to Invoice | Quantity Invoiced | Production Plan No. | Production Plan Qty.
2/16/2020 | Item | ZAEV001 | Meal Breakfast (.650 KG PACK) | 610001 | 10 | PAX | 45 | 450 | 10 |  | 10 | PPN0005 | 10
2/16/2020 | Item | ZAEV002 | Meal Lunch (.800 KG PACK) | 610001 | 15 | PAX | 50 | 750 |  |  | 15 | PPN0006 | 15
2/17/2020 | Item | ZAEV001 | Meal Breakfast (.650 KG PACK) | 610001 | 11 | PAX | 45 | 495 |  |  | 11 | PPN0007 | 11
2/17/2020 | Item | ZAEV002 | Meal Lunch (.800 KG PACK) | 610001 | 16 | PAX | 50 | 800 |  |  | 16 | PPN0008 | 16

## s1.2
Banquet Enquiry page
General
Field |  | Existing | Tab |  | Field |  |  | Existing | Tab
Type of sale |  | Yes | General |  | Customer No |  |  | Yes | General
Type of Event |  | Yes | Event Info |  | Customer Name |  |  | Yes | General
Event |  | Yes | Event Info |  | Inquiry company No. |  |  | No |  | (Lookup from Contact List Type=Company), If customer no exist, then non-editable.
Detail of the event |  | Yes | Event Info |  | Inquiry company Name |  |  | No
Segment |  | Yes | Event Info |  | Inquiry contact No. |  |  | No |  | (Lookup from Contact List Type=Person), If customer no exist, then non-editable.
Location BEO |  | Yes | Event Info |  | Inquiry contact Name |  |  | No
Status of Event |  | Yes | General | (*Remove Full Deliver; Partial Deliver; Full Invoice; Partial Invoice); Validate when Status of Event = Definite "Customer No should not be blank.
Revision |  | Yes | General
Prepared By |  | Yes | General
Pricing and Billing (Inquiry)
No. of PAX |  | Yes | Pricing and Billing
Average Price Per PAX/FB |  | Yes | Pricing and Billing
Transport Amount |  | Yes | Pricing and Billing
Staff (Amount) |  | Yes | Pricing and Billing
Banquet Enquiry list
No. | Type of sale | Type of event | Enent | Segment | Location BEO | Status of Event | Customer No | Customer Name | Avergae Price Per PAX/FB | Transport Amount | Staff Amount

## s1.1
Release | Posting Shipment | Order | Request Approval | Navigate
General Tab
Sales Order Number / BEO # |  |  | Status Field |  | ** | Non-editable
Type of Sale |  |  | Transaction status of event |  | **
Organization Name |  |  | Revision
Contact Name |  |  | Project ID
Phone Numbers: |  |  | Project Name
Email Address: |  |  | Date of function start:
SalesPerson |  |  | Date of function end:
Prepared by: |  |  | Start Timing: | Line1 Line2 (Min 5 Line) Line3 Line4
Method of Receiving Enquiry
Order date
Posting date |  |  | End Timing: | Line1 Line2 (Min 5 line) Line3
Location Code
Event Info
Event |  |  | Venue:
Details of the event | Line1 Line2 (Min 10 line) Line3 |  | Location (BEO):
|  |  | Service Delivery | Line1 Line2 (Min 10 line) Line3
Type of Event
Type of Event (Brief) |  |  | Service Style | Line1 Line2 (Min 10 line) Line3
Segment
Guests
Guest Guaranteed
Guest Expexted
HK Lines
Pricing and Billing
Pricing and Billing (Revenue report) For Grouping |  |  | Pricing and Billing (Invoice) For Grouping
No. of PAX |  |  | Menu Price
Average Price Per PAX/F&B |  |  | Pricing | Line1 Line2 (Min 10 line) Line3
Transport (Amount)
Staff (Amount)
|  |  | Billing Instruction: | Line1 Line2 (Min 5 line) Line3
Food and Beverage
Food Menus: | Line1 Line2 Line3 Line4 (Min 100 Line Option) |  | Beverages: | Line1 Line2 Line3 Line4 (Min 50 Line Option)
|  |  | Food and Beverage Notes: | Line1 Line2 (Min 10 Line Option)
Setup and Equipment Notes
Kithcen: | Line1 Line2 (Min 10 line) Line3 |  | Housekeeping | Line1 Line2 (Min 10 line) Line3
Equipment: | Line1 Line2 (Min 10 line) Line3 |  | Transportation/Security | Line1 Line2 (Min 10 line) Line3
Stewarding: | Line1 Line2 (Min 10 line) Line3 |  | Engineering | Line1 Line2 (Min 10 line) Line3
Restriction/Special Reference | Line1 Line2 (Min 10 line) Line3 |  | Additional Instructions | Line1 Line2 (Min 10 line) Line3
Setup notes: | Line1 Line2 (Min 10 line) Line3 |  | Hygiene | Line1 Line2 (Min 10 line) Line3
Staffing: | Line1 Line2 (Min 10 line) Line3 |  | Reffered By

## c2
FRD List
FRD/RC/CST-003-1 | Production plan
Separate production plan to be generated for each BEO Meal line. (Separate porduction plan for each date and meal type).
1. Custom table required (Header and Line Format)
Header fields:
| Field | Detail
| Production plan no. | From No. Series (Auto generate)
| Bulk Kitchen Location | Lookup from Location list (Location Type Filter= Bulk Location)
| Delivery Date | Based on BEO Line No, Shipment date (Non-Editable) | Editable: User select date in this field.
| BEO no. | Look up field from BEO list. Only BEO with status confirmed should be visible. | Confirmed;
| BEO Line No. | Look up from Sales Order Line (BEO). | Filter on BEO No + Date (Validation : Not Already Selected)
| Project no. | Update from BEO. No option to change here, should update in BEO and from BEO update here.
| Meal Description | Based on BEO Line No, Meal Item Description
| No. of PAX | Based on BEO Line No, Remaining Qty To Ship (Non-Editable)
Open; Inprocess; Posted
| Recipe Cost | Flow field from (Qty x Recipt Cost)
Line field:
| Field | Detail
| Item | Lookup from item list. On item card, some field to identy, if allowd to select in production plan list.
| Description | Description from item card.
| UoM | On item card, one field required to select Production Plan UoM. Update UoM from Production plan UoM.
| Qty. | Quantity as per Production Plan UoM.
| Recipe Cost | Item Card, converted as per UoM conversion.
| **Calculate standard cost | Yes/No
| **Calculate standard cost run date | Date on which Adjust cost Item Entry is run.
| Option to copy from same project |  | Filter based on project
Option to upload from excel.
Header
| Production Plan No. | BEO no. | Project no. | Kitchen Location | Meal Description | Delivery Date | No. of PAX | Status:
| PPN0005 | BEO-0001 | Ferrari World | Mustaffa Bulk Kitchen | 0 | #REF! | 0 | Delivered
| Item | Description | UoM | Qty. | Recipe Cost | **Calculate standard cost | **Calculate standard cost run date
| Recipe Item A |  | KG | 35 | 10
| Recipe Item B |  | KG | 45 | 15
| BEO no. | Project no. | Kitchen Location | Meal period | Date | No. of PAX | Status:
| BEO-0001 | Project A | Mustaffa Bulk Kitchen | Lunch | 2020-03-23 | 45 | Delivered
| Item | Description | UoM | Qty. | Recipe Cost | **Calculate standard cost | **Calculate standard cost run date
| Recipe Item A |  | KG | 45 | 10
| Recipe Item D |  | KG | 45 | 15

## c3
FRD List
FRD/RC/CST-003-2 | Auto cost booking (Trf to CPU Kitchen/Project Kitchen)
Location card:
Custom Filed: Kitchen Bulk Cost/Kitchen Project Cost
Cost Dimension: Select Bulk cost dimnesion/or Project Dimension depending on project type.
Transfer Order:
Any transfer to Bulk cost (Common Kitchen) or Project cost, negative journal (Sales/COGS) to passed with dimension on location card.
Technical team can suggest, location wise separate Item Journal template to be used, or same Item Journal Template can be used.

## c4
FRD List
FRD/RC/CST-003-3 | Auto cost booking (Direct purchase at CPU Kitchen/Project Kitchen)
Location card:
Custom Filed: Kitchen Bulk Cost/Kitchen Project Cost
Cost Dimension: Select Bulk cost dimnesion/or Project Dimension depending on project type.
Purchase order:
If purchase order is booked to Kitchen Bulk cost/Kitchen Project Cost location, negative adjustment entry (sale/COGS) to be passed with dimension on location card.
Negative adjustment entry to be passed on product receipt posting.
Option required to select, rejected qty and split PO line. Reject Qty to be transfereed to reject location

## c5
FRD List
FRD/RC/CST-003-4 | Cost sheet table and Journal Posting
FRD/RC/CST-003-4.1 | Cost sheet Table
Cost sheet table is to save the Bulklocation+Date wise cost allocation and posting detail.
Generate cost sheet:
System to check, for To Date and Location, costsheet is already generated.
New cost sheet for the same location, after To Date.
Before cost sheet generartion, system to run the folowing cost batches:
System will run Adjust cost item entries first`
Then run Calc. Standard Cost for item BoM Exist and Blocked =No.
Header
| From Date | To Date | Kitchen Location | Bulk Allocation Cost | Journal Created | Voucher No. (Pre) | Journal Posted | Voucher No. (Posted)
| 2020-03-22 | 2020-03-22 | Mustaffa Kitchen | 100000 | Yes/No |  | Yes/No
Line
| Project Dimension | Recipe Cost | Allocation % | Accocated Cost | Accocated Cost manual
| Project A | 25000 | 27.78 | 27780 | 35000
| Project B | 65000 | 72.22 | 72220 | 65000
90000
Header
| From Date: | Select From Date. (From date should be after To Date of last cost shhet for same bulk location.
| To Date: | Select to date.
| Kitchen location: | From Location list (Location Type: Bulk cost location)
| Bulk allocation cost: | From COGS ledger net balance with filter Date+Bulk Cost Dimension. In inventory setup, option to select ledger COGS.
| Journal created: | Yes/No (When journal entry is created.)
Voucher No. (Pre)
Voucher No. (Posted)
Lines
| Project Dimension: | Based on date and location filter. From Production Plan.
| Recipe cost | From production plan.
| Allocation % | From production plan. Based on recipe cost ratio. Rounded off to two decimal and total should be equal to 100.
| Allocated cost | Bulk cost amount x Allocated cost. Rounded off to 2 decimal and total should be equal to bulk allocation cost.
| Allocated cost manula | By default same as Allocated cost. Edit option avbl. Total should equal to Bulk allocation cost.
FRD/RC/CST-003-4.2 | Create and post journal lines
Based on cost sheet generated, create journal lines. Journal lines should be non-editable.
Journal line should be blank (Posted), to create new journal lines.
Journal template and batch from location card.
| Date | Account | Dimension | Amount
| 2020-03-22 | Bulk Cost Ledger | Mustaffa Kitchen | -100000 | Cr
| 2020-03-22 | Bulk Cost Ledger | Project A | 35000 | Dr
| 2020-03-22 | Bulk Cost Ledger | Project B | 65000 | Dr
| Date: | To Date of cost sheet.
| Account: | Bulk cost ledger from Inventory setup.
| Dimension: | Line1: Bulk cost from
System should update, project plan for which cost sheet is generated.
System should update, GL entry for which cost sheet is generated.
System should update Cost Sheet No. in GL entry table for :
1. Bulk cost posting entries considered for Bulk allocation cost amount.
2. Project wise cost allocation journal.
FRD/RC/CST-003-4.3 | Default setup for cost sheet and cost journal
Inventory setup:
| Kitchen cost account: | Select the Kitchen cost/COGS account here.
Location card:
| Cost Template: | Select cost template.
| Cost Batch | Select cost batch.
Separate template and batch for each cost location.
Note: This journal template and batch, should not be avbl. in Standard General Journal.
Separate page to open Cost Allocation Journal Template.
Formulas:
To Date = [From Date]

## p1
FRD List
FRD/RC/PUR-001 | Purchase requisition workflow and approval and Purchase Quote
User/Department wise separate Template and batch is created in system.
User security required on Template. #Customisation
Requisition line history to be mentained when requisition is converted to quote/order. And status field to be maintained.
Notification to Requestor, other concerned people and purchaser if workflow is approved and to Requestor and other concerned people, if rejected.
Deligation option required.
If against a project, select project location and project dimension to auto update from location, this project location and dimension will carry forward till purchase order.
Delivery date field, when material is required.
Business Justification field, text field 250 character.
In location field select direct delivery location. If material is received at warehouse and then transferred to project location, then select warehouse location in location field and In Transfer To Location, select final delivery location.
| Option1: | Requester will create multiple item lines with the template and batch.
Requester will select the lines which he want to send for approval.
Requirement: Only selected lines will go to approval, based on approval setup.
Approval setup can be based on item category; User; Dimension.
Lines send for apporval should be non-editable and only apporver can change or modify.
Requester can see only those line which are pending for apporval.
Notification: Single notification entry for multiple lines. And single e-mail notofication.
Approver side:
Apporver can select on the email link or notification to access the Template.
Apporver can see only those lines which are send for approval.
He can select all lines and apporve or reject, or line wise.
| Option2: | Create separate batch for new requisition entry.
New batch creation customization will be required.
Batch level workflow and apporval required.
Requester:
Send batch for apporval, batch will be non-editable for all users, except Approver.
Approver:
Notofication and e-mail at batch level to apporver.
Approver can access the batch and reject or approve whole batch.
| Option3: | Custom table for purchase requisition with Header and Line (for each purchase requisition).
Submit for quote/purchase order
All apporved requisition lines appear in single list.
Based on Requestor ID, Location ID or Item Cateogry

## p1.1
Purchase requisition and Workflow approval
PR | Purchse requisition required in Header and Line format.
One purchase requisition, with multiple item line.
Header level approval (Same as purchase order, All Base approval workflow and notification required).
Single notification and mail at Header level.
PR-Header | Two separate page for Replishment Type= Purchase and Transfer
Purchase requisition created by me (Preparer Filter)
Requisition Table
| Replishment Type: |  |  |  |  | Requested date:
| Purchase requisition No: |  |  |  |  | Preparer:
| Name: |  | Single line (100 Ch) |  |  | Reason code:
Requester:
| Status: |  |  |  |  | Detail: |  | Single line (250 Ch)
| Receiving Location: |  |  |  |  | Item Category Code:
Transfer from Location:
PR-Line | Requisition lines
| Type | No | Description |  |  | Quantity | UoM | Unit Price | Item Category |  | Requester | Line Status
| Item | ITM0011 | [5 empty] | ????
Field Detail (Header):
Replishment System: Purchase (Auto update from Page)
Purchase requisition No: No. series from Purchase and Payble setup.
Name: Text field (100 Ch)
Requester Name: Lookup from Purchaser Code/Sales person code (Show description here)
Requisition Status: Draft; Submit; Approved; Rejected;
Transaction Status: Approved (Ordered); Approved (Partially Ordered); Received; Received (Partially); Invoiced; Invoiced (Partially)
Status field should update from requisition line (If all lines are apporved, then Header Status is approved; If All lines are received then Received etc.
Receiving Location: Lookup from location list.
Transfer from Location: Refer logic of Transfer from location in Requisition worksheet.
Delivery date: Date on which delivery is expected.
Preparer: User ID of person, creating requistion.
Purchaser Code: Look up from User list. (Auto update from custom table)
Reason code: Look up from lookup list.
| Detail: | Text field (250 ch)
Item Category Code: If not selected blank.
Field Detail (Line)
Type: Item; GL; FA; Comment (Refer Requistion worksheet line)
Item Category Code: From header.
No.:Item filter based on Item Category Code.
Description: Text field (100 Ch), update from item; GL; FA; Comment code
Unit of Measure Code: Refer requisition worksheet line.
Quantity: Number field
Direct Unit Cost: Refer requisition worksheet Direct Unit Cost Field (Non editable field).
Approved requisition wooksheet
RL-Approved | Once Approved, Requisitio worksheet is updated with approved requisition lines.
Page: Purchase requisition assigned to me (Purchase code filter)
Once requisition line is created, user cant delete the line, user can change the status Open; Purchase order Created; Quotation Created; Transfer Order Created; Canceled.
| Type | Item Category Code | No. | Purchaser Code | Action Message | Accept Action Message | Description | Transfer from Location | Location Code | Original Quantity | Quantity | Unit of Measure Code | Direct Unit Cost | Vendor Purchase Price exist | Order Date | Original Due Date | Delivery date | Vendor No. | Replenishment System | Ref. Order Type | Ref. Order No. | Ref. Line No. | Planning Flexibility | Confirmed | Requisition Header | Requisition Line | Approved Requisition Line Status
| Item |  | ZY001 |  |  | Yes | ItemA |  | 10MUWEH01 | X | 10 | PCS | 0 | Yes/No | 2020-07-04 |  | 2020-10-04 | V00020 | Purchase | x | x | x | x | x
|  |  |  | (Base Requester ID) |  |  |  | (Refer Transfer from Location on Requisition worksheet) | [7 empty] | (Base Due Date)
Requisition worksheet lines:
Type: From purchase requisition lines.
Item Category Code: Requisition line.
No.: From purchase requisition lines.
Purchaser Code: From User List (Based on custom table explained below).
Accept Action Message: Yes
Description: From requisition lines
Location: from purchase requisition line.
Transfer from location: Refer Transfer from Location on Requisition worksheet (Editable field)
Quantity: From Purchase requisition line.
Unit of Measure Code: From purchase requisition line.
Delivery date: From requisition line (Base due date).
Order date: Base Order date.
Vendor No.: Base vendor No.
Replishment system: From purchase requisition line.
Requisition Header: From requisition table.
Requisition Line: From requisition table.
Apporved requisition line Status: Once requisition line is created, user cant delete the line, user can change the status to Cancel (Other status =Open; Purchase order Created; Quote Created; Transfer Order Created; Canceled).
PT | Purchaser table:
| Location | Item Category | Purchaser Code
Priority1: Location + Item Category
Priority2: Location
Prioroty3: Item Category
Priority4: Blank
Quote | Condition to create quote (from Purchase and Payable Setup):
Condition 1: Create quote for all = Yes/No
Condition 2: Create quote for item category/item: Yes/No
Condition 3: Vendor Trade Agreement exist = Yes/No"
(Only one condition will be activated/checked by the system)
Grouping: | Purchase order line grouping (Purchase and Payable Setup):
Grouping based on item=Yes/No
Groping based on delivery date: Yes/No
Purchase Quote line grouping (Purchase and Payable Setup):
Grouping based on item=Yes/No
Groping based on delivery date: Yes/No
Transfer order line grouping:
Grouping based on item=Yes/No
Groping based on delivery date: Yes/No
Update fields same as Purchase order.
When user click on button to create document:
System should show one option box:
Create Purchase order:
Purchase order header grouping:
Replishment Type: Purchase Order
Vendor: Separate Order for each vendor
Location: Separate Order for each location.
Order Date From: (Editable)
Order Date To: (Editable)
Purchase order line grouping:
Item: Yes/No (From Purchase and Payable Setup (Editable)
Delivery Date: Yes/No (From Purchase and Payable Setup (Editable)
Create purchase quote:
Purchase quite will be created for the item lines (approved requisition lines) manually selected by user. If user want to create single quote, for multiple item, user have to select the items manually.
Purchase quote header grouping:
Replishment Type: Purchase Quote
Vendor: Separate quote for each vendor
Location: Separate quote for each location.
Purchase quote line grouping:
Item: Yes/No (From Purchase and Payable Setup (Editable)
Delivery Date: Yes/No (From Purchase and Payable Setup (Editable)
Create Transfer order:
Purchase quote header grouping:
Replishment Type: Transfer order
Transfer from location & Transfer To Location:
Order Date From: (Editable)
Order Date To: (Editable)
Transfer order line grouping:
Item: Yes/No (From Purchase and Payable Setup (Editable)
Delivery Date: Yes/No (From Purchase and Payable Setup (Editable)

## testig
Requisition Line |  | Unit of Measure
Vendor No.
Currency Code
Due Date (deliver date)
Order date
Vendor No.
Varient Code
Requisition Line |  | Unit of measure = logic same as req. w.sheet
Remove currency code
Remove Buy From Vendor
Remove Unit Price
Requisition Line |  | Document Type: Purchase order; Purchase quote; Transfer order; Cancel
Document No
Document Line No
**Partial received; Full received; Partial Invoice; Full Invoiced
Approved requisitip: |  | Separate button for Create purchase order; Create Quote; Create Transfer Order
Purchase order header grouping:
Replishment Type: Purchase Order
Vendor: Separate Order for each vendor
Location: Separate Order for each location.
Order Date From: (Editable)
Order Date To: (Editable)
Purchase order line grouping:
Item: Yes/No (From Purchase and Payable Setup (Editable)
Delivery Date: Yes/No (From Purchase and Payable Setup (Editable)
Apporved requistion to PO:
Expected receipt date on line : Lowest receipt date
| 1 | Item Grp=Yes |  | Grp on Item
Delivery Date Grp=No
| 2 | Item Grp=Yes |  | Grp on delivery date
Delivery Date Grp=Yes
| 3 | Item Grp=No |  | Separet line for each req line
Delivery Date Grp=No
18-04-2020 Requisition
Cancel disable after release
Release should not allowed to edit
Release Document should not allowed to send for aproval
Cancel approval request not working.
Locationwise purchases= Change name to "Requisition Purchaser setup"
Apporved requisition: Order date field not updated properly based on Due date (Receipt date)
Apporved requisition: Change Due Date field name to Receipt date
Apporved requisition: Update purchaser code on requisition line. And fileter on Purchase code
Page: Purchase requisition assigned to me (with Purchase code filter) and Purchase requisition-All (Without purchase requisiiton fileter)
Apporved requisition to Order: Condition 1 Item Grp=Yes and Delivery Date Grp=No (if multiple item not working)
Apporved requisition to Order: Date filter type= Order date/Receipt date
Apporved requisition to Order: Selected lines
Purchase order: Expected receipt date on header (Lowest receipt date from all lines)
Purchase order: Assigned ueser ID=Purchase code

## P2
Purchase order mail send status
Email to vendor, with email ID from vendor card.
Email to Warehouse/store incharge, with email ID from location.
Email to requisition user.
On purchase and payable setup, one text field to enter mail body (min 5 line 100 Character each).
On purchase order header, option to edit this mail text.
(Note: Mail body text or format required for RC team)
When user click on send mail button, system will show mail body and Purchase order preview and ask for send mail Yes or No.
If user click Yes (mail is send to vendor and concerned people.

## p3
FRD List
FRD RC PUR-001-3 | Based on active price agreement exist or Not
A | 1. If trade agreement exists, then auto approval. System will check Vendor Price group in the Vendor card
B | 2. If trade agreement does not exist, then approval based on purchase order amount (as per current process). •PO-: 0-3K AED (Approval defined User) •PO-: 3K-20K AED (Approval Supply Chain Manager) •PO-: 20K-50K AED (Approval Supply Chain Manager-CFO) •PO-: Above 50KAED (Approval Supply Chain Manager-CFO-CEO)
If purchase price is updated from Vendor Price Table, then Vendor Trade Agreement=Yes, else No.
If Vendor price agreement is Yes , for all lines then Auto Apporove PO.
If Vendor price agreement is No , then apporval based on Hierarchy.
Vendor Price
| Vendor No. | Item No. | Unit of Measure Code | Minimum Quantity | Direct Unit Cost | Starting Date | Ending Date
| V00020 | FD2440 | KG | 0 | 1000 | 2020-01-01 | 4/30/2020
| Type | No. | Description | Location Code | Bin Code | Quantity | Reserved Quantity | Unit of Measure Code | Direct Unit Cost Incl. VAT | Line Amount Incl. VAT | Vendor Trade Agreement
| Item | FD2440 | PICKLE ARABIC 6 KG ( MIX) - SYRIA | 20MUKIT01 |  | 60 |  | BKT | 4.725 | 269.32 | Yes
| Item | FD2440 | PICKLE ARABIC 6 KG ( MIX) - SYRIA | 20MUKIT01 |  | 40 |  | BKT | 4.725 | 179.55 | No
| Item | FD1088 | Corman Wipping Cream 1x1ltr | 20MUKIT01 |  | 10 |  | LTR | 0.63 | 6.05 | No

## p4
Rejected Qty Field and Auto Trf. To Reject Location
Justification: Any direct purchase to Bulk Kitchen or Project Kitechen, as per customization, system will pass negative adjustment (cost entry) for all OK and rejected Qty.
Requirement: Only OK Qty to be considered for negative adjustment (cost entry) and rejected qty to be returned to vendor through Credit Note.
On Purchase order, a new column will be provided, Rejected Qty.
|  | Original Quantity | Received Qty | Reject Qty
| PO Line | 10 | 10 | 2
On product receipt, system will receive all 10 qty, in actula location, PO line location field.
Before passing, ingative adjustment for Kitchen location, system will pass a reclass entry for Rejected Qty. item journal (Cost entry) for remaining 8 OK qty.

## p5
Allow over delivery qty
• Over Delivery % define in the Purchase & Payable setup
In the Purchase Order Line over delivery allow on the % allowed in Purchase & Payable setup
For Example
| Set up | Filed | Value
| Purchase & Payable setup | Over delivery | 5%
| Quantity Orderd | 100
| Quantity Received | 105 | Over delivery (System should allow)
| Qty. to Invoice | 105
| Quantity Invoiced | 105
System through error in case of over delivery allow above define % in Purchase & Payable setup

## p6
FRD List | Short delivery (Close PO Process)
New column on Purchase order line Under Delivery (Not to Receive).
In this field user will entry the under delivery qty., which we will not receive in futute.
On periodic basis user will a batch to close all PO's which have fully invoice, or Only under delivery qty is pending.
Condition to close PO:
Condition 1: PO Qty for all PO line = or < Invoice Qty for PO line
Condition 2: PO Qty for all PO line = or < Invoice Qty for PO line + Under Delivery Qty.

## m1
FRD List
FRD/RC/MAN-001 | Maintenance service
• Service Order Form raise service Request
• Raise Purchase Requisition for service item
• Requisition and Purchase Approval require
• Purchase requisition as explained by Procurement dept.
• Inventory to be maintain in ERP
• Project Dimension to cost control
• Option to load cost on project/location based on usage/consumption. (For Financial reporting/profitability report).
Additional Fields required for maintaining breakdown tracking
Fields | Description
MRO No. | Maintenance request order no.
Asset ID | Option to select FA ID. One MRO = One FA ID will be maintained.
Asset ID | mandatory and can be blank.
Duration From | Service request order date.
Duration To | Closing date.
Equipment | Auto update from Asset ID description, editable.
Location | Auto update from Asset card (Location Field), editable.
Break Duration | No. of Days between Duration To and Duration From.
Details | Text field (250 character).
Consequences | Option Field (Major; Minor; Moderate).
Corrective action plan | Text field (250 character).
Preventive action plan | Text field (250 character).
Material cost | Service item used or consumed.
Manpower cost | Amount Field (To be entered manually.)
LPO No. | Text field 100 Character (One MRO will have multiple LPO.)
Status | Open; In-process; On Hold; Closed.
Remarks | Text field (100 character).
Report to be Develop

## f1
FRD List
FRD/RC/FIN-003 | Post Dated Cheque
• PDC Ledger Given in Purchase & Payable setup
• Need a PDC Register report by customer/Vendor as on date
| PDC Ledger | 11100089 | PDC Account
| • Vendor Card | PDC Vendor | Boolean
When Raise the invoice against this vendor
PDC Payment at that time capturing the legder from Purchase and Payable setup
Accounting Entry
PDC Payment
| Date | Particular | Dr. | Cr.
| 2020-03-01 | Vendor | XXXX
| 2020-03-01 | To PDC |  | XXXX
At the Time of clearance
| Date | Particular | Dr. | Cr.
| 2020-03-05 | PDC | XXXX
| 2020-03-05 | To Bank |  | XXXX

## f2
FA as inventoty item
FA item to be maintained as inventory item.
User will create a FA card and For each FA one item card.
User will attach Item card to FA card.
Also on FA card/FA Category one check box, Maintain FA item inventory
Custom field require to attach or Tag Item to FA.
Financial entries to be captured as per FG module.
For FA Item, inventory will be maintained at zero value.
FA Item can be transferred, negative adjustment entry can be passed to maintan actaul physical inventory.
And Location wise inventroy report required for these FA Item.
If on FA card/FA Category, Maintain FA Item Inventoty =Yes
On Purchase order/invoice posting, system should pass Positive adjustment entry, to maintain FA Inventory.
Item Journal Fields:
| Date | Invoice posting date
| Item | From FA card
| Qty | PO/Invoice Qty
| Unit Price | 0
| Location | Purchase invoice location
| Dimension | From Purchase Invoice

## Report 1
FRD List
Sr. No | Report | Date | Technical Person | Tested By | Status | Remarks
1 | Delivery Note
2 | Event Order Sheet (BEO)
3 | Tax Invoice
4 | Catch Invoice
5 | Item Journal
6 | packing slip summary
7 | packing slip
8 | sales order
9 | Transfer order-Shipment
10 | Cost Allocation
11 | Tax Invoice
12 | Purchase Order
13 | Category wise/Vendor wise/UoM Wise Item Qty and Cost
14 | Breakdown monitoring report (Maintenance)
15 | Check Printing Report • AL Mashraf Bank-Arbift (Format Shared) • NBF Bank (Format Shared)
16 | PDC Register