## Sheet1
Time Sheet for March 2020
APLICA |  |  |  |  | Address1 | Aplica Tech Global Pvt Ltd.
Name | Suraj Srivastava |  |  |  | Address2
Client Name | Royal Catering |  |  |  | Address3
Project Code & Description |  | Project Desc | Customization of costing, project wise and Item wise
Client Project Manager
Month & Year | March | 2020
Date | Start Time | End Time | No of Hrs | Description of Tasks Performed | Remarks | Status
2020-03-13 | 10:00 | 13:00 | 3 | Purchase Order Report layout Design and customization in Purchase Order Card (Addition of report in Action) | Layout design and data Item integration | Inprogress
2020-03-14 |  |  | WeekEnd
2020-03-15 |  |  | WeekEnd
2020-03-16 | 10:00 | 16:00 | 5 | Purchase Order Report layout Design and customization in Purchase Order Card (Addition of report in Action) | Addition of Report in the Action tab and alignment of design | Inprogress
2020-03-17 | 14:00 | 18:00 | 4 | Purchase Order Report layout Design and customization in Purchase Order Card (Addition of report in Action) | Calculation and logic with layout fixing | Completed
2020-03-18 | 10:00 | 19:00 | 6 | TAX Invoice Report design and indetation |  | Inprogress
2020-03-19 | 10:30 | 15:00 | 5 | Layout design and new fields addition in report | Layout design and data Item integration | Inprogress
2020-03-20 | 10:00 | 14:00 | 4 | Tax Calculation and discount % calculation with value of line amount and overall amount including Tax | Caculation and logic implemation | Completed
2020-03-21 |  |  | WeekEnd
2020-03-22 |  |  | WeekEnd
2020-03-23 | 10:00 | 17:00 |  | Customization list discussion |  | Inprogress
2020-03-24 | 10:00 | 19:00 |  | Customization list discussion |  | Inprogress
2020-03-25 | 10:00 | 19:00 | 9 | Estimation over customization along with asign task |  | Completed
2020-03-26 | 10:00 | 19:00 | 9 | Make projects as a dimension, with few new fields for detailed information about the projects. New table for production Plan , Like Production Plan Header and Production Plan lines. | Addition of new fields like status, from and to date, kitchen location etc. | Completed
2020-03-27 | 10:00 | 19:00 | 9 | Separate Page, List psrt and card Page has created and calculation over recipe costing | Sepearte item has a separate standard cost to be maintain for recipe calculation | Completed
2020-03-28 | 12:00 | 18:00 | 5 | Auto calculation of standard cost for each item present in Production plan Lines | Calculation of standard cost of each item and upation in production plan Lin | Completed
2020-03-29 |  |  | WeekEnd
2020-03-30 | 10:00 | 19:10 | 9.1 | New field addtion in Location Card Like Location Type , Template and Batches Etc. also given the relation with production plan, also separate codeunit for auto negative Adjustment through Item journal while posting the Transfer Order from Warehouse Location to Kitchen Location |  | Inprogress
2020-03-31 | 10:00 | -
2020-04-01
2020-04-02
2020-04-03
2020-04-04
2020-04-05
2020-04-06
2020-04-07
2020-04-08
2020-04-09
2020-04-10
2020-04-11
2020-04-12
2020-04-13
2020-04-14
2020-04-15
2020-04-16
2020-04-17
2020-04-18
2020-04-19
2020-04-20
2020-04-21
2020-04-22
2020-04-23