## FRD List
FRD No. | FRD Description | FDD No. | FDD Description | Sheet No. | Type | Technical Effort (Hrs) | Hours Spent | Remarks | Technical Assigned | Start Date | End Date | Technical Status | Functional Testing By | Functional Testing Status | CRP Ststus
FRD/RC/CST-003 | Food cost and cost allocation | FRD/RC/CST-003-0 | Project wise cost | c1 | Customization
|  |  | Enter project detail | j1 | Customization | 4 | 3 |  | Suraj | 2020-03-26 | 2020-03-26 | Completed | Santhosh
FRD/RC/SAL-001 | Sales cycle (Contract) | FRD/RC/SAL-001-1 | Create Banquet Event Order | s1 | Customization | 24 |  |  | sunil | 2020-03-27 | 2020-03-31
FRD/RC/CST-003 | Food cost and cost allocation | FRD/RC/CST-003-1 | Production plan | c2 | Customization | 14 | 16 |  | suraj | 2020-03-26 | 2020-03-27 | Completed | Santhosh
FRD/RC/CST-003 | Food cost and cost allocation | FRD/RC/CST-003-2 | Auto cost booking (Trf to CPU Kitchen/Project Kitchen) | c3 | Customization | 10 | 8 |  | suraj | 2020-03-30 | 2020-03-31 | Inprogress | Santhosh
FRD/RC/CST-003 | Food cost and cost allocation | FRD/RC/CST-003-3 | Auto cost booking (Direct purchase at CPU Kitchen/Project Kitchen) | c4 | Customization | 20 |  |  | Sunil | 2020-04-01 | 2020-04-03
FRD/RC/CST-003 | Food cost and cost allocation | FRD/RC/CST-003-4 | Cost sheet report and Journal Posting | c5 | Customization | 16 |  |  | Suraj | 2020-04-01 | 2020-04-02
FRD RC PUR-001 | Purchase Requisition | FRD RC PUR-001-1 | Purchase requisition workflow and approval | p1 | Customization | 20 |  |  | Suraj | 2020-04-03 | 2020-04-07
| RFQ |  | Request for Quote |  | Customization | 10 |  |  | Suraj | 2020-04-08 | 2020-04-09
FRD RC PUR-001 | Purchase order |  | Purchase order - Send to Vendor status and send mail through outlook. | p2 | Customization | 10 |  |  | Sunil | 2020-04-06 | 2020-04-07
FRD RC PUR-001 | Purchase order |  | Purchase order approval based on Trade Price exist or Not. | p3 | Customization | 10 |  |  | Sunil | 2020-04-07 | 2020-04-08
FRD RC PUR-001 | Purchase order |  | Rejected Qty Field and Auto Trf. To Reject Location | p4 | Customization | 14 |  |  | Sunil | 2020-04-09 | 2020-04-10
| Purchase order |  | Over delivery | p5 |  | 14 |  |  | Suraj | 2020-04-10 | 2020-04-13
| Purchase order |  | Short delivery (Close PO Process) | p6 |  | 10 |  |  | Suraj | 2020-04-13 | 2020-04-14
FRD/RC/MAN-001 | Maintenance service | FRD/RC/MAN-001-1 | Maintenance service | m1 | Customization | 12 |  |  | Suraj | 2020-04-15 | 2020-04-16
FRD/RC/FIN-003 | Post Dated Cheque | FRD/RC/FIN-003-1 | Process of Post dated cheque | f1 | Customization | 20 |  |  | Sunil | 2020-04-13 | 2020-04-15
| Facility management |  | Facility management (Fields requred for sales invoice) |  | Customization | 4 |  |  | Sunil | 2020-04-16 | 2020-04-16
| General Journal Workflow |  | General Journal Workflow (Batch Customization) Copy from VX Studio |  | Customization | 10 |  |  | Sunil | 2020-04-16 | 2020-04-17
| Fixed Asset |  | Fixed asset as inventory item | f2 | Customization | 14 |  |  | Suraj | 2020-04-17 | 2020-04-20
| Delivery Note |  |  | r1 | Reports | 16 |  |  | Suraj | 2020-04-21 | 2020-04-22
| Event Order Sheet (BEO) |  |  | r2 | Reports | 20 |  |  | Suraj | 2020-04-23 | 2020-04-27
| Tax Invoice |  |  | r3 | Reports | 16 |  |  | suraj |  |  | InProgress | Pradeep
| Tax Invoice (facility Management) |  |  | r77 | Reports | 12 |  |  | Sunil | 2020-04-22 | 2020-04-23
| Catch Invoice |  |  | r4 | Reports | 10 |  |  | Sunil | 2020-04-23 | 2020-04-24
| Item Journal |  |  | r5 | Reports | 16 |  |  | Suraj | 2020-04-28 | 2020-04-29
| packing slip summary |  |  | r6 | Reports | 12 |  |  | Suraj | 2020-04-30 | 2020-05-01
| packing slip |  |  | r7 | Reports | 10 |  |  | Suraj | 2020-05-01 | 2020-05-04
| sales order |  |  | r8 | Reports |  |  | Need clarity Pending for customization | Sunil
| Transfer order-Shipment |  |  | r9 | Reports | 10 |  |  | Sunil | 2020-04-27 | 2020-04-28
| Cost Allocation |  |  | r10 | Reports | 16 |  |  | Sunil | 2020-04-28 | 2020-04-30
| Purchase Order |  |  | r12 | Reports | 10 |  |  | Suraj |  |  | Completed | Pradeep
| Category wise/Vendor wise/UoM Wise Item Qty and Cost |  |  | r13 | Reports | 16 |  |  | Suraj | 2020-05-05 | 2020-05-06
| Breakdown monitoring report (Maintenance) |  |  | r14 | Reports | 14 |  |  | Suraj | 2020-05-07 | 2020-05-08
| Check Printing Report • AL Mashraf Bank-Arbift (Format Shared) • NBF Bank (Format Shared) |  |  | r15 | Reports | 10 |  |  | Suraj | 2020-05-09 | 2020-05-10
| PDC Register |  |  | r16 | Reports | 8 |  |  | Sunil | 2020-05-01 | 2020-05-01
| Voucher print |  | Copy from VX Studio | r18 | Reports | 10 |  |  | Sunil | 2020-05-04 | 2020-05-05
| Tax Register |  |  |  | Reports | 10 |  | Format /Column not finalised | Sunil | 2020-05-05 | 2020-06-06
| Average price per item |  |  |  | Reports | 10 |  |  | Sunil | 2020-05-07 | 2020-05-08

## c1
FRD List
Food cost and cost allocation-Project wise cost
1.1 For any new contract/project dimension is created.
1.2 Account schedule will be used for Project wise revenue and expenses.
1.3 System should also provide, project wise sales invoice; BEO; purchases (if direct purchase); item journal.
While configuration/customization, should keep in mind, possibility of generating following data/report (other than mentioned in FRD)
Project wise invoice and receipt.
Project wise BEO list.
Project wise item journal detail.
Project wise direct purchase order.
Project wise JV expenses.
Project wise revenue and expense report from sales; General ledger and item ledger table.

## j1
FRD/RC/CST-003-1.1 | Project Dimension and Project Mapping
| Custom table to maintain project dimension wise default value. |  |  |  | Table
Either a custom table or Base Project table to capture the following default details:
Project start date
Project end date
| Project status | Open; Inporcess; Hold; Closed
Kitchen Location
Only one project dimension + project combination should exit in system.
Table
| Project Dimension | Project No.
Ferrari World
| Jobs |  | Dimension need to add
|  |  | comment | Attachment also

## s1
FRD List
FRD/RC/SAL-001 | Sales cycle (Banquet Event Order)
FRD/RC/SAL-001-1 | Capture contract detail in system.
• Create Sales Order | New Option Field : Banquet Event Order
• Fill Contract Details
• Require Custom from | Custom
• In Sales Header (Customise Field)-Update BEO Status require Given Option-: Open order/Confirmed//Delivered/Invoiced/Cancelled | Custom
• In Sales Header BEO version to be Maitain (On any Modifiaction) .i.e. Version 1, 2 | Base archive version to be used.
• In Sales order form (Above) option require (i.e. Copy BEO Information) (Information that captured in previouse BEO -Same Project | Custom
Fields Name | Type | No. of Line | No. of Characters | Remarks
Event: | Lookup field | NA | NA
Type of Event | Text Fields
Menu Price | Text Fields |  | 100 | Customer Card
Contact Name | Customer Card | NA | NA
Prepared by: | Lookup field |  |  | Employee List
Organization Name | Automatic' |  |  | Customer Card
Phone Numbers: | Customer Card | NA | NA | Customer Card
Email Address: | Customer Card | NA | NA | Customer Card
Sales Order Number / BEO # | No. Series | NA | NA | No. Series
Revision | Revision | NA | NA
Project ID | Dimension | NA | NA
Project Name | Dimension Name | NA | NA
date of function start: | Date Filed | NA | NA
date of function end: | Date Filed | NA | NA
Start Timing: | Text Fields | 5 | 50
End Timing: | Text Fields | 5 | 50
Venue: | Text Fields | 1 | 100
pricing | Text Fields | 1 | 100
Location: | Text Fields | 1 | 100
Guest Guaranteed | Text Fields | 1 | 50 Each Line
Guest Expexted | Text Fields | 1 | 50 Each Line
Service Delivery | Text Fields | 10 | 100
Service Style | Text Fields | 10 | 100
Food Menus: | Text Fields | 100 | 5000
Beverages: | Text Fields | 1 | 50
Food & Beverages Notes: | Text Fields | 10 | 100
Kithcen: | Text Fields | 10 | 100
Equipment: | Text Fields | 10 | 100
Stewarding: | Text Fields | 5 | 100
restriction: | Text Fields | 7 | 100
Details of the event | Text Fields | 10 | 100
Set Up: | Text Fields | 10 | 100
Staffing: | Text Fields | 2 | 100
Housekeeping | Text Fields | 1 | 100
Transportation | Text Fields | 5 | 100
Engineering | Text Fields | 1 | 100
Additional | Text Fields | 10 | 100
Billing Instruction: | Text Fields | 5 | 100

## c2
FRD List
FRD/RC/CST-003-1 | Production plan
1. Custom table required (Header and Line Format)
Header fields:
| Field | Detail
| Production plan no. | From No. Series (Auto generate)
| BEO no. | Look up field from BEO list. Only BEO with status confirmed should be visible.
| Project no. | Update from BEO. No option to change here, should update in BEO and from BEO update here.
| Kitchen Location | From project table. (Non-editable)
| Meal period | Option filed : Breakfast/Lunch/Dinner/Midnight/Others | To be discussed
| Date | Option to select date. By default Work date. (Should be between BEO Start Date and End Date). | To be discussed
| No. of PAX | Number field. (Auto update, non-editable) | To be discussed
| Status: | Open; Inprocess; Delivered | To be discussed
| Recipe Cost | Flow field from (Qty x Recipt Cost)
| Note: System should check combination of Project no.+BEO no.+Meal Period+Date, in production plan header table. |  | Rewirk
If same combination exist then system should give error and should not allow to continue or save.
Line field:
| Field | Detail
| Item | Lookup from item list. On item card, some field to identy, if allowd to select in production plan list. And restrict the blocked Items as well.
| Description | Description from item card.
| UoM | On item card, one field required to select Production Plan UoM. Update UoM from Production plan UoM.
| Qty. | Quantity as per Production Plan UoM.
| Recipe Cost | Item Card, converted as per UoM conversion.
| **Calculate standard cost | Yes/No
| **Calculate standard cost run date | Date on which Adjust cost Item Entry is run.
| Option to copy from same project | Production Plan Lines
| Option to upload from excel. | (Other than
| BEO no. | Project no. | Kitchen Location | Meal period | Date | No. of PAX | Status:
| BEO-0001 | Project A | Mustaffa Bulk Kitchen | Breakfast | 2020-03-23 | 45 | Delivered
| Item | Description | UoM | Qty. | Recipe Cost | **Calculate standard cost | **Calculate standard cost run date
| Recipe Item A |  | KG | 35 | 10
| Recipe Item B |  | KG | 45 | 15
| BEO no. | Project no. | Kitchen Location | Meal period | Date | No. of PAX | Status:
| BEO-0001 | Project A | Mustaffa Bulk Kitchen | Lunch | 2020-03-23 | 45 | Delivered
| Item | Description | UoM | Qty. | Recipe Cost | **Calculate standard cost | **Calculate standard cost run date
| Recipe Item A |  | KG | 45 | 10
| Recipe Item D |  | KG | 45 | 15
Item Card
| Rolled up material Cost Field | add
| Recipe Item | Boolean | new
| Production Plan UOM | Table Relation Unit of Measurement | new
CalculateStdCost: Codeunit "Calculate Standard Cost";
Clear(CalculateStdCost);
CalculateStdCost.CalcItem("No.", false);

## c3
FRD List
FRD/RC/CST-003-2 | Auto cost booking (Trf to CPU Kitchen/Project Kitchen)
Location card:
Custom Filed: Kitchen Bulk Cost/Kitchen Project Cost/Blank(default)
Cost Dimension: Select Bulk cost dimnesion/or Project Dimension depending on project type.
Transfer Order:
Any transfer to Bulk cost (Common Kitchen) or Project cost, negative journal (Sales/COGS) to passed with dimension on location card.
Technical team can suggest, location wise separate Item Journal template to be used, or same Item Journal Template can be used.
| Template | To Location
| Batch | To Location
| Posting Date | Entry Type | Document No. | Item No. | Description | Location Code | Quantity | Unit of Measure Code | Unit Amount | Amount | Discount Amount | Unit Cost | Applies-to Entry | Project Code
| 2/16/2020 | Sale | T00008 | ZARM001 | Rice A | 20MUKIT01 | 2 | KG | 0 | 0 | 0 | 28.21 | 0 | 8810001
| 2/16/2020 | Sale | T00008 | ZARM002 | Rice B | 20MUKIT01 | 2 | KG | 0 | 0 | 0 | 21.45 | 0 | 8810001
| Receipt posting date | Sale | Defaule | TO Line | NA | To Locatuon | TO Line Qty | TO Line UoM | NA | NA | NA | NA | NA | To Location Project Dimension

## c4
FRD List
FRD/RC/CST-003-3 | Auto cost booking (Direct purchase at CPU Kitchen/Project Kitchen)
Location card:
Custom Filed: Kitchen Bulk Cost/Kitchen Project Cost
Cost Dimension: Select Bulk cost dimnesion/or Project Dimension depending on project type.
Purchase order:
If purchase order is booked to Kitchen Bulk cost/Kitchen Project Cost location, negative adjustment entry (sale/COGS) to be passed with dimension on location card.
Negative adjustment entry to be passed on product receipt posting.
Option required to select, rejected qty and split PO line. Reject Qty to be transfereed to reject location

## c5
FRD List
FRD/RC/CST-003-4 | Cost sheet table and Journal Posting
FRD/RC/CST-003-4.1 | Cost sheet Table
Cost sheet table is to save the Bulklocation+Date wise cost allocation and posting detail.
Generate cost sheet:
System to check, for To Date and Location, costsheet is already generated.
New cost sheet for the same location, after To Date.
Before cost sheet generartion, system to run the folowing cost batches:
System will run Adjust cost item entries first`
Then run Calc. Standard Cost for item BoM Exist and Blocked =No.
Header
| From Date | To Date | Kitchen Location | Bulk Allocation Cost | Journal Created | Voucher No. (Pre) | Journal Posted | Voucher No. (Posted)
| 2020-03-22 | 2020-03-22 | Mustaffa Kitchen | 100000 | Yes/No |  | Yes/No
Line
| Project Dimension | Recipe Cost | Allocation % | Accocated Cost | Accocated Cost manual
| Project A | 25000 | 27.78 | 27780 | 35000
| Project B | 65000 | 72.22 | 72220 | 65000
90000
Header
| From Date: | Select From Date. (From date should be after To Date of last cost shhet for same bulk location.
| To Date: | Select to date.
| Kitchen location: | From Location list (Location Type: Bulk cost location)
| Bulk allocation cost: | From COGS ledger net balance with filter Date+Bulk Cost Dimension. In inventory setup, option to select ledger COGS.
| Journal created: | Yes/No (When journal entry is created.)
Voucher No. (Pre)
Voucher No. (Posted)
Lines
| Project Dimension: | Based on date and location filter. From Production Plan.
| Recipe cost | From production plan.
| Allocation % | From production plan. Based on recipe cost ratio. Rounded off to two decimal and total should be equal to 100.
| Allocated cost | Bulk cost amount x Allocated cost. Rounded off to 2 decimal and total should be equal to bulk allocation cost.
| Allocated cost manula | By default same as Allocated cost. Edit option avbl. Total should equal to Bulk allocation cost.
FRD/RC/CST-003-4.2 | Create and post journal lines
Based on cost sheet generated, create journal lines. Journal lines should be non-editable.
Journal line should be blank (Posted), to create new journal lines.
Journal template and batch from location card.
| Date | Account | Dimension | Amount
| 2020-03-22 | Bulk Cost Ledger | Mustaffa Kitchen | -100000 | Cr
| 2020-03-22 | Bulk Cost Ledger | Project A | 35000 | Dr
| 2020-03-22 | Bulk Cost Ledger | Project B | 65000 | Dr
| Date: | To Date of cost sheet.
| Account: | Bulk cost ledger from Inventory setup.
| Dimension: | Line1: Bulk cost from
System should update, project plan for which cost sheet is generated.
System should update, GL entry for which cost sheet is generated.
System should update Cost Sheet No. in GL entry table for :
1. Bulk cost posting entries considered for Bulk allocation cost amount.
2. Project wise cost allocation journal.
FRD/RC/CST-003-4.3 | Default setup for cost sheet and cost journal
Inventory setup:
| Kitchen cost account: | Select the Kitchen cost/COGS account here.
Location card:
| Cost Template: | Select cost template.
| Cost Batch | Select cost batch.
Separate template and batch for each cost location.
Note: This journal template and batch, should not be avbl. in Standard General Journal.
Separate page to open Cost Allocation Journal Template.
Formulas:
To Date = [From Date]

## p1
FRD List
FRD/RC/PUR-001 | Purchase requisition workflow and approval and Purchase Quote
User/Department wise separate Template and batch is created in system.
User security required on Template. #Customisation
Requisition line history to be mentained when requisition is converted to quote/order. And status field to be maintained.
Notification to Requestor, other concerned people and purchaser if workflow is approved and to Requestor and other concerned people, if rejected.
Deligation option required.
If against a project, select project location and project dimension to auto update from location, this project location and dimension will carry forward till purchase order.
Delivery date field, when material is required.
Business Justification field, text field 250 character.
In location field select direct delivery location. If material is received at warehouse and then transferred to project location, then select warehouse location in location field and In Transfer To Location, select final delivery location.
| Option1: | Requester will create multiple item lines with the template and batch.
Requester will select the lines which he want to send for approval.
Requirement: Only selected lines will go to approval, based on approval setup.
Approval setup can be based on item category; User; Dimension.
Lines send for apporval should be non-editable and only apporver can change or modify.
Requester can see only those line which are pending for apporval.
Notification: Single notification entry for multiple lines. And single e-mail notofication.
Approver side:
Apporver can select on the email link or notification to access the Template.
Apporver can see only those lines which are send for approval.
He can select all lines and apporve or reject, or line wise.
| Option2: | Create separate batch for new requisition entry.
New batch creation customization will be required.
Batch level workflow and apporval required.
Requester:
Send batch for apporval, batch will be non-editable for all users, except Approver.
Approver:
Notofication and e-mail at batch level to apporver.
Approver can access the batch and reject or approve whole batch.
| Option3: | Custom table for purchase requisition with Header and Line (for each purchase requisition).
Submit for quote/purchase order
All apporved requisition lines appear in single list.
Based on Requestor ID, Location ID or Item Cateogry

## P2
Purchase order mail send status
Email to vendor, with email ID from vendor card.
Email to Warehouse/store incharge, with email ID from location.
Email to requisition user.
On purchase and payable setup, one text field to enter mail body (min 5 line 100 Character each).
On purchase order header, option to edit this mail text.
(Note: Mail body text or format required for RC team)
When user click on send mail button, system will show mail body and Purchase order preview and ask for send mail Yes or No.
If user click Yes (mail is send to vendor and concerned people.

## p3
FRD List
FRD RC PUR-001-3 | Based on active price agreement exist or Not
A | 1. If trade agreement exists, then auto approval. System will check Vendor Price group in the Vendor card
B | 2. If trade agreement does not exist, then approval based on purchase order amount (as per current process). •PO-: 0-3K AED (Approval defined User) •PO-: 3K-20K AED (Approval Supply Chain Manager) •PO-: 20K-50K AED (Approval Supply Chain Manager-CFO) •PO-: Above 50KAED (Approval Supply Chain Manager-CFO-CEO)
If purchase price is updated from Vendor Price Table, then Vendor Trade Agreement=Yes, else No.
If Vendor price agreement is Yes , for all lines then Auto Apporove PO.
If Vendor price agreement is No , then apporval based on Hierarchy.
Vendor Price
| Vendor No. | Item No. | Unit of Measure Code | Minimum Quantity | Direct Unit Cost | Starting Date | Ending Date
| V00020 | FD2440 | KG | 0 | 1000 | 2020-01-01 | 4/30/2020
| Type | No. | Description | Location Code | Bin Code | Quantity | Reserved Quantity | Unit of Measure Code | Direct Unit Cost Incl. VAT | Line Amount Incl. VAT | Vendor Trade Agreement
| Item | FD2440 | PICKLE ARABIC 6 KG ( MIX) - SYRIA | 20MUKIT01 |  | 60 |  | BKT | 4.725 | 269.32 | Yes
| Item | FD2440 | PICKLE ARABIC 6 KG ( MIX) - SYRIA | 20MUKIT01 |  | 40 |  | BKT | 4.725 | 179.55 | No
| Item | FD1088 | Corman Wipping Cream 1x1ltr | 20MUKIT01 |  | 10 |  | LTR | 0.63 | 6.05 | No
trigger OnAction()
var
ReleasePurchDoc: Codeunit "Release Purchase Document";
begin
ReleasePurchDoc.PerformManualRelease(Rec);
end;
trigger OnAction()
var
ReleasePurchDoc: Codeunit "Release Purchase Document";
begin
ReleasePurchDoc.PerformManualReopen(Rec);
end;

## p4
Rejected Qty Field and Auto Trf. To Reject Location
Justification: Any direct purchase to Bulk Kitchen or Project Kitechen, as per customization, system will pass negative adjustment (cost entry) for all OK and rejected Qty.
Requirement: Only OK Qty to be considered for negative adjustment (cost entry) and rejected qty to be returned to vendor through Credit Note.
On Purchase order, a new column will be provided, Rejected Qty.
|  | Original Quantity | Received Qty | Reject Qty
| PO Line | 10 | 10 | 2
On product receipt, system will receive all 10 qty, in actula location, PO line location field.
Before passing, ingative adjustment for Kitchen location, system will pass a reclass entry for Rejected Qty. item journal (Cost entry) for remaining 8 OK qty.

## p5
Allow over delivery qty
• Over Delivery % define in the Purchase & Payable setup
In the Purchase Order Line over delivery allow on the % allowed in Purchase & Payable setup
For Example
| Set up | Filed | Value
| Purchase & Payable setup | Over delivery | 5%
| Quantity Orderd | 100
| Quantity Received | 105 | Over delivery (System should allow)
| Qty. to Invoice | 105
| Quantity Invoiced | 105
System through error in case of over delivery allow above define % in Purchase & Payable setup

## p6
FRD List | Short delivery (Close PO Process)
New column on Purchase order line Under Delivery (Not to Receive).
In this field user will entry the under delivery qty., which we will not receive in futute.
On periodic basis user will a batch to close all PO's which have fully invoice, or Only under delivery qty is pending.
Condition to close PO:
Condition 1: PO Qty for all PO line = or < Invoice Qty for PO line
Condition 2: PO Qty for all PO line = or < Invoice Qty for PO line + Under Delivery Qty.

## m1
FRD List
FRD/RC/MAN-001 | Maintenance service
• Service Order Form raise service Request
• Raise Purchase Requisition for service item
• Requisition and Purchase Approval require
• Purchase requisition as explained by Procurement dept.
• Inventory to be maintain in ERP
• Project Dimension to cost control
• Option to load cost on project/location based on usage/consumption. (For Financial reporting/profitability report).
Additional Fields required for maintaining breakdown tracking
Fields | Description
MRO No. | Maintenance request order no.
Asset ID | Option to select FA ID. One MRO = One FA ID will be maintained.
Asset ID | mandatory and can be blank.
Duration From | Service request order date.
Duration To | Closing date.
Equipment | Auto update from Asset ID description, editable.
Location | Auto update from Asset card (Location Field), editable.
Break Duration | No. of Days between Duration To and Duration From.
Details | Text field (250 character).
Consequences | Option Field (Major; Minor; Moderate).
Corrective action plan | Text field (250 character).
Preventive action plan | Text field (250 character).
Material cost | Service item used or consumed.
Manpower cost | Amount Field (To be entered manually.)
LPO No. | Text field 100 Character (One MRO will have multiple LPO.)
Status | Open; In-process; On Hold; Closed.
Remarks | Text field (100 character).
Report to be Develop

## f1
FRD List
FRD/RC/FIN-003 | Post Dated Cheque
• PDC Ledger Given in Purchase & Payable setup
• Need a PDC Register report by customer/Vendor as on date
| PDC Ledger | 11100089 | PDC Account
| • Vendor Card | PDC Vendor | Boolean
When Raise the invoice against this vendor
PDC Payment at that time capturing the legder from Purchase and Payable setup
Accounting Entry
PDC Payment
| Date | Particular | Dr. | Cr.
| 2020-03-01 | Vendor | XXXX
| 2020-03-01 | To PDC |  | XXXX
At the Time of clearance
| Date | Particular | Dr. | Cr.
| 2020-03-05 | PDC | XXXX
| 2020-03-05 | To Bank |  | XXXX

## f2
FA as inventoty item
FA item to be maintained as inventory item.
User will create a FA card and For each FA one item card.
User will attach Item card to FA card.
Also on FA card/FA Category one check box, Maintain FA item inventory
Custom field require to attach or Tag Item to FA.
Financial entries to be captured as per FG module.
For FA Item, inventory will be maintained at zero value.
FA Item can be transferred, negative adjustment entry can be passed to maintan actaul physical inventory.
And Location wise inventroy report required for these FA Item.
If on FA card/FA Category, Maintain FA Item Inventoty =Yes
On Purchase order/invoice posting, system should pass Positive adjustment entry, to maintain FA Inventory.
Item Journal Fields:
| Date | Invoice posting date
| Item | From FA card
| Qty | PO/Invoice Qty
| Unit Price | 0
| Location | Purchase invoice location
| Dimension | From Purchase Invoice

## Report 1
FRD List
Sr. No | Report | Date | Technical Person | Tested By | Status | Remarks
1 | Delivery Note
2 | Event Order Sheet (BEO)
3 | Tax Invoice
4 | Catch Invoice
5 | Item Journal
6 | packing slip summary
7 | packing slip
8 | sales order
9 | Transfer order-Shipment
10 | Cost Allocation
11 | Tax Invoice
12 | Purchase Order
13 | Category wise/Vendor wise/UoM Wise Item Qty and Cost
14 | Breakdown monitoring report (Maintenance)
15 | Check Printing Report • AL Mashraf Bank-Arbift (Format Shared) • NBF Bank (Format Shared)
16 | PDC Register